## Slide 1
MY GRADUATE PROGRAM TIMELINE
PhD in Technology · Purdue Polytechnic Institute · Spring 2026 – Fall 2029
Md Kamruzzaman Kamrul
Bowen School of Construction Management Technology
Advisor: Dr. Heung Jin Oh · Wii Lab · CSE Concentration
103
TOTAL CREDITS
21
TRANSFER (GSU)
41
PURDUE COURSEWORK
41
DISSERTATION
4 YRS
DURATION
Transfer (GSU)
Current (Sp 2026)
Planned Courses
Dissertation Research
Milestone

## Slide 2
MY GRADUATE PROGRAM TIMELINE
Kamruzzaman Kamrul · PhD Technology · Purdue · Spring 2026 – Fall 2029
Sp'26
Su'26
Fa'26
Sp'27
Su'27
Fa'27
Sp'28
Su'28
Fa'28
Sp'29
Su'29
Fa'29
TRANSFER
GSU MS Transfer — 7 Courses (21 cr)
CORE REQUIRED
TECH 60300 Grad Seminar Planning (1cr)
MET 52700 Technology: Global Perspective (3cr)
STAT 50100 Experimental Statistics I (3cr)
TECH 60100 Research Seminar (1cr)
TECH 64600 Analysis of Research in Industry (3cr)
TECH 67600 Analysis of Research Methods (3cr)
TECH / DISCOVERY
STAT 52000 Time Series & Applications (3cr)
STAT 52400 Applied Multivariate Analysis (3cr)
STAT 51400 Design of Experiments (3cr)
CSE CONCENTRATION
CS 57800 Statistical Machine Learning (3cr)
CS 52000 Computational Optimization (3cr)
ECE 57000 Artificial Intelligence (3cr)
GRAD 68900 CSE Seminar 0cr (recurring)
COGNATE ELECTIVES
CS 59300 Computer Vision (3cr)
ECE 59500 Selected Topics in ECE (3cr)
CS 58000 Algorithm Design & Analysis (3cr)
DISSERTATION
TECH 69900 Dissertation Research: Phases 1-6
Prelim Exam
Proposal Defense, Data Collection
Writing
Final Defense
Transfer Credits
Current (Sp'26)
Planned Courses
Dissertation Research
Milestone

## Slide 3
4-YEAR PATH: PHASES & KEY DELIVERABLES
Each milestone builds on prior coursework with specific outputs
PHASE 1: FOUNDATION
Sp'26 – Sp'27
• Front-load core & tech courses
• Begin literature review (200+ papers)
• Establish committee
• Research problem identification
✓ Research direction approved
PHASE 2: QUALIFICATION
Su'27 – Fa'27
• Co-op internship (Jun-Aug)
• Prelim exam preparation
• Methodology development
• Complete preliminary research outline
★ PRELIM EXAM (Fa 27)
PHASE 3: PROPOSAL
Sp'28 – Fa'28
• Write proposal (30-50 pages)
• Finalize research design & methods
• Plan data collection strategy
• Prepare proposal defense
★ PROPOSAL DEFENSE (Fa 28)
PHASE 4: COMPLETION
Sp'29 – Fa'29
• Intensive data collection & analysis
• Write Ch 1-4 (Intro, Lit, Methods, Results)
• Dissertation composition
• Final defense & graduation
★ FINAL DEFENSE (Fa 29)

## Slide 4
KEY MILESTONES: REQUIREMENTS & RATIONALE
PRELIMINARY EXAM (Fall 2027)
Requirement
Written comprehensive exam + Oral defense + Committee approval
Deliverables
Pass both written + oral exams | Submit approved outline | Committee signs candidacy
Timeline
End of Year 2 (Semester 5) — Standard PhD progression
Intensity
20+ hours/week — Focused on exam prep & research design
PROPOSAL DEFENSE (Fall 2028)
Requirement
Defend 30-50 page proposal with full committee
Deliverables
Present & defend proposal | Submit approved document | Committee approves method
Timeline
12 months after Prelim — Allows methodology development
Intensity
18-20+ hours/week — Proposal writing + preliminary data collection
DATA COLLECTION & ANALYSIS (Sp-Su 2029)
Requirement
Acquire, validate, and analyze dissertation dataset(s)
Deliverables
Complete ≥1 validated dataset | Preprocessing pipeline documented | Results generated
Timeline
Semesters 9-10 — Peak research phase
Intensity
25+ hours/week (peak) — Full-time research focus
FINAL DEFENSE (Fall 2029)
Requirement
Oral defense & approval of completed dissertation
Deliverables
Final dissertation approved by committee | Pass oral defense | ETD submission
Timeline
End of Year 4 (Semester 11) — 4-year completion
Intensity
25+ hours/week — Final writing, revisions, defense prep

## Slide 5
COURSE INVENTORY & CREDIT BREAKDOWN
TRANSFER — GSU MS (21 cr)
CIS 8005 Data Programming (3cr)
CIS 8398 Advanced AI for Business (3cr)
CIS 8695 Big Data Analytics (3cr)
CIS 8795 Big Data Infrastructure (3cr)
CIS 8080 IS Security & Privacy (3cr)
CIS 8045 Unstructured Data Management (3cr)
CIS 8690 Topics in Information Systems (3cr)
SPRING 2026 — Current (10cr)
STAT 52000 Time Series & Applications (3cr)
CS 59300 Computer Vision (3cr)
ECE 59500 Selected Topics in ECE (3cr)
TECH 60300 Grad Seminar – Planning (1cr)
FALL 2026 (10cr)
MET 52700 Technology: Global Perspective (3cr)
STAT 50100 Experimental Statistics I (3cr)
TECH 60100 Research Seminar in Technology (1cr)
TECH 64600 Analysis of Research in Industry (3cr)
SPRING 2027 (9cr)
TECH 67600 Analysis of Research Methods (3cr)
CS 57800 Statistical Machine Learning (3cr)
CS 52000 Computational Optimization (3cr)
SUMMER 2027 — CO-OP
Industry Internship (3 months)
FALL 2027 — ★ Prelim Exam
STAT 52400 Applied Multivariate Analysis (3cr)
GRAD 68900 CSE Seminar (0cr)
SPRING 2028 — Proposal Writing (3cr)
STAT 51400 Design of Experiments (3cr)
GRAD 68900 CSE Seminar (0cr)
SUMMER 2028 — Proposal Dev
TECH 69900 Dissertation (proposal draft)
FALL 2028 — ★ Proposal Defense
ECE 57000 Artificial Intelligence (3cr)
GRAD 68900 CSE Seminar (0cr)
SPRING 2029 — Data Collection
CS 58000 Algorithm Design & Analysis (3cr)
GRAD 68900 CSE Seminar (0cr)
SUMMER 2029 — Analysis & Writing
TECH 69900 Dissertation (analysis phase)
FALL 2029 — ★ FINAL DEFENSE 🎓
TECH 69900 Dissertation Defense
Graduation
CREDIT SUMMARY: Transfer GSU 21cr + Purdue Coursework 41cr + Dissertation 41cr = 103cr Listed | Graduation: Fall 2029

## Slide 6
PROFESSIONAL DEVELOPMENT & IDP GOALS
GOAL 1: ACADEMIC PUBLICATIONS
Timeline: Phase 1-4 publications integrated into research phases
Target: 5+ journal articles + 5+ conference papers by graduation
Plan: Phase 1 (1 paper) → Phase 2 (1-2) → Phase 3 (2-3) → Phase 4 (1-2 final)
Status: ✓ On track (publications embedded in Gantt)
GOAL 2: TECHNICAL MASTERY
Deep Learning: CS 59300 (Vision), CS 57800 (ML), ECE 57000 (AI)
Time Series: STAT 52000, STAT 52400, STAT 51400
Optimization: CS 52000, CS 58000
Target: 300 LeetCode problems + Cloud cert by Summer 2027
Status: ✓ Courses front-loaded; co-op summer for coding sprint
GOAL 3: INDUSTRY EXPERIENCE
Co-op Internship: Summer 2027 (3 months, Jun-Aug)
Placement: Strategic gap between foundation & prelim phases
Focus: Industry tech skills (cloud ML, DevOps, data engineering)
Future: Internship opportunities in Year 3-4 as time permits
Status: ✓ Scheduled; aligns with post-co-op CSE courses (Fa27 onward)