## Slide 1
MY GRADUATE PROGRAM TIMELINE
PhD in Technology · Purdue Polytechnic Institute · Spring 2026 – Fall 2029
Md Kamruzzaman Kamrul
Bowen School of Construction Management Technology
Advisor: Dr. Heung Jin Oh · Wii Lab · CSE Concentration
103
TOTAL CREDITS
21
TRANSFER (GSU)
41
PURDUE COURSEWORK
41
DISSERTATION
4 YRS
DURATION
Transfer (GSU)
Current (Sp 2026)
Planned Courses
Dissertation Research
Milestone

## Slide 2
MY GRADUATE PROGRAM TIMELINE
Kamruzzaman Kamrul · PhD Technology · Purdue · Spring 2026 – Fall 2029
Sp'26
Su'26
Fa'26
Sp'27
Su'27
Fa'27
Sp'28
Su'28
Fa'28
Sp'29
Su'29
Fa'29
TRANSFER
GSU MS Transfer — 7 Courses (21 cr)
CORE REQUIRED
TECH 60300 Grad Seminar Planning (1cr)
MET 52700 Technology: Global Perspective (3cr)
STAT 50100 Experimental Statistics I (3cr)
TECH 60100 Research Seminar (1cr)
TECH 64600 Analysis of Research in Industry (3cr)
TECH 67600 Analysis of Research Methods (3cr)
TECH / DISCOVERY
STAT 52000 Time Series & Applications (3cr)
STAT 52400 Applied Multivariate Analysis (3cr)
STAT 51400 Design of Experiments (3cr)
CSE CONCENTRATION
CS 57800 Statistical Machine Learning (3cr)
CS 52000 Computational Optimization (3cr)
ECE 57000 Artificial Intelligence (3cr)
GRAD 68900 CSE Seminar 0cr (recurring)
COGNATE ELECTIVES
CS 59300 Computer Vision (3cr)
ECE 59500 Selected Topics in ECE (3cr)
CS 58000 Algorithm Design & Analysis (3cr)
DISSERTATION
TECH 69900 Dissertation Research: Phases 1-6
Prelim Exam
Proposal Defense
Data Collection
Writing
Final Defense
Transfer Credits
Current (Sp'26)
Planned Courses
Dissertation Research
Milestone

## Slide 3
MILESTONE DELIVERABLES & TIMELINE
FALL 2027 — PRELIMINARY EXAM
✓ Pass written comprehensive exam
✓ Pass oral defense with committee
✓ Approved prelim outline & research plan
⏱ Semester 5 | 2.5 years into PhD
📊 Research Intensity: 20+ hrs/week
FALL 2028 — PROPOSAL DEFENSE
✓ Defended dissertation proposal (30-50 pages)
✓ Approved methodology & research design
✓ Approved data collection strategy
⏱ Semester 8 | 12 months after Prelim
📊 Research Intensity: 20+ hrs/week
SPRING-SUMMER 2029 — DATA COLLECTION
✓ ≥1 complete dataset acquired & validated
✓ Data preprocessing pipeline documented
✓ Preliminary empirical results generated
⏱ Semesters 9-10 | Post-proposal phase
📊 Research Intensity: 25+ hrs/week (peak)
SUMMER-FALL 2029 — WRITING & DEFENSE
✓ Ch 1-3 draft: Intro, Literature, Methods
✓ Ch 4 draft: Empirical Results & Analysis
✓ Full dissertation completed & approved
✓ Final defense completed & passed
✓ ETD submitted, graduation approved

## Slide 4
COURSE INVENTORY & CREDIT BREAKDOWN
TRANSFER — GSU MS (21 cr)
CIS 8005 Data Programming (3cr)
CIS 8398 Advanced AI for Business (3cr)
CIS 8695 Big Data Analytics (3cr)
CIS 8795 Big Data Infrastructure (3cr)
CIS 8080 IS Security & Privacy (3cr)
CIS 8045 Unstructured Data Management (3cr)
CIS 8690 Topics in Information Systems (3cr)
SPRING 2026 — Current (10cr)
STAT 52000 Time Series & Applications (3cr)
CS 59300 Computer Vision (3cr)
ECE 59500 Selected Topics in ECE (3cr)
TECH 60300 Grad Seminar – Planning (1cr)
FALL 2026 (10cr)
MET 52700 Technology: Global Perspective (3cr)
STAT 50100 Experimental Statistics I (3cr)
TECH 60100 Research Seminar in Technology (1cr)
TECH 64600 Analysis of Research in Industry (3cr)
SPRING 2027 (9cr)
TECH 67600 Analysis of Research Methods (3cr)
CS 57800 Statistical Machine Learning (3cr)
CS 52000 Computational Optimization (3cr)
SUMMER 2027 — CO-OP
Industry Internship (3 months)
FALL 2027 — ★ Prelim Exam
STAT 52400 Applied Multivariate Analysis (3cr)
GRAD 68900 CSE Seminar (0cr)
SPRING 2028 — Proposal Writing (3cr)
STAT 51400 Design of Experiments (3cr)
GRAD 68900 CSE Seminar (0cr)
SUMMER 2028 — Proposal Dev
TECH 69900 Dissertation (proposal draft)
FALL 2028 — ★ Proposal Defense
ECE 57000 Artificial Intelligence (3cr)
GRAD 68900 CSE Seminar (0cr)
SPRING 2029 — Data Collection
CS 58000 Algorithm Design & Analysis (3cr)
GRAD 68900 CSE Seminar (0cr)
SUMMER 2029 — Analysis & Writing
TECH 69900 Dissertation (analysis phase)
FALL 2029 — ★ FINAL DEFENSE 🎓
TECH 69900 Dissertation Defense
Graduation
CREDIT SUMMARY: Transfer GSU 21cr + Purdue Coursework 41cr + Dissertation 41cr = 103cr Listed | Graduation: Fall 2029