## Slide 1
MY GRADUATE PROGRAM TIMELINE
Version 4 - Handbook-aligned prelim dependencies - Spring 2026 to Fall 2029
Md Kamruzzaman Kamrul
PhD in Technology - Purdue Polytechnic Institute - CSE Concentration
Advisor: Dr. Heung Jin Oh - Wii Lab - Bowen School of Construction Management Technology
103
TOTAL CREDITS
21
TRANSFER (GSU)
41
PURDUE COURSEWORK
41
DISSERTATION
4 YRS
TARGET DURATION
Transfer
Current
Coursework
Admin/Prereq
Prelim
Research

## Slide 2
VERSION 4 GANTT CHART: COURSEWORK, PRELIM DEPENDENCIES, RESEARCH
Handbook checkpoints added: approved POS, committee, reading list, written/oral prelim, Form 10, retake window
Sp'26
Su'26
Fa'26
Sp'27
Su'27
Fa'27
Sp'28
Su'28
Fa'28
Sp'29
Su'29
Fa'29
TRANSFER
GSU MS transfer credits - 7 courses / 21 cr
COURSEWORK
Sp'26 current: TECH603(1), STAT520(3), CS593(3), ECE595(3)
Fa'26 core: MET527(3), STAT501(3), TECH601(1), TECH646(3)
Sp'27 methods/ML: TECH676(3), CS578(3), CS520(3)
Su'27 compressed electives: STAT514(3), CS580(3)
Fa'27 final prelim-semester courses: STAT524(3), ECE570(3)
GRAD689 CSE seminar - 0 cr recurring
PRELIM DEPS
Advisor topic/timeline meetings; GPA/core grade check
Plan of Study + prelim committee finalized (3+ faculty)
Develop reading list from research topic (10+ weeks out)
Submit reading list 9 weeks out; committee review/revise
Questions finalized + dept review; written component
Written review, oral exam, official result, Form 10
CONTING
Retake window if needed - next immediate semester
RESEARCH
Research foundation: literature, problem framing, pilot ideas
Prelim synthesis + proposal outline
Proposal development: design, methods, committee feedback
Data collection and analysis
Dissertation writing, revisions, defense preparation
POS + course audit
Prelim Exam
Retake if needed
Proposal Defense
Final Defense
Transfer
Current
Coursework
Admin/Prereq
Prelim
Research
Contingency

## Slide 3
PRELIMINARY EXAM HANDBOOK TIMELINE
Fall 2027 target with relative deadlines from the approved Polytechnic handbook
1. Eligibility Gates
- Approved Plan of Study.
- Good standing: 3.0+ GPA.
- No unresolved core grade below B-.
- Required courses complete or in progress.
- Committee: 3+ graduate faculty; majority regular.
2. Reading List
- Meet advisor on topic and timeline.
- Develop topic-linked list at least 10 weeks out.
- Submit to committee exactly 9 weeks out.
- Committee reviews/revises within 2 weeks.
3. Written Component
- Questions finalized from approved list.
- Chair sends questions for department review.
- Complete written responses within 6 weeks.
- Submit responses immediately on completion.
4. Oral + Result
- Committee reviews written work within 2 weeks.
- Written result sent within 1 week.
- If approved, oral exam scheduled within 2 weeks.
- If both approved, Chair submits electronic Form 10.
Fall 2027 dependency chain for the Gantt milestone
-10 wks
Reading list draft
-9 wks
Submit list
-7 wks
List approved
-6 wks
Questions to dept
Exam
Written component
+2 wks
Committee review
+4 wks
Oral exam
+1 wk
Form 10
Pass Path
Written and oral components must both be Approved in the same administration.
Retake Rule
If Not Approved, the second prelim should be completed by Spring 2028; summer does not count as the next immediate semester.
Defense Guardrail
Final defense in Fall 2029 leaves far more than two registration sessions after the Fall 2027 prelim.

## Slide 4
KEY MILESTONES: REQUIREMENTS, DEPENDENCIES, OUTPUTS
AUG 2027 - POS + COURSEWORK AUDIT
Requirement
Approved POS, committee plan, GPA/core-grade review, and final prelim-semester course plan locked.
Why placed here
Confirms handbook eligibility before the reading-list clock starts.
FALL 2027 - PRELIMINARY EXAM
Requirement
Reading list approved; written response completed; oral component passed; Chair submits electronic Form 10.
Why placed here
Moves the plan from coursework-heavy preparation into proposal development.
SPRING 2028 - RETAKE WINDOW IF NEEDED
Requirement
Second prelim only if written or oral component is Not Approved in Fall 2027.
Why placed here
Handbook requires the second administration by the next immediate semester; summer does not apply.
FALL 2028 - PROPOSAL DEFENSE
Requirement
Finalize research design, methods, data plan, committee feedback, and IRB/data protocol if applicable.
Why placed here
Creates a clean handoff into Spring-Summer 2029 data collection and analysis.
FALL 2029 - FINAL DEFENSE + ETD
Requirement
Complete dissertation, defend, address revisions, submit ETD, and clear graduation requirements.
Why placed here
Final milestone stays at the end and satisfies the post-prelim registration-session spacing rule.

## Slide 5
COURSE INVENTORY & CREDIT BREAKDOWN
Coursework is front-loaded so the Fall 2027 prelim has the handbook prerequisites in place.
TRANSFER - GSU MS (21 cr)
CIS 8005 Data Programming (3cr)
CIS 8398 Advanced AI for Business (3cr)
CIS 8695 Big Data Analytics (3cr)
CIS 8795 Big Data Infrastructure (3cr)
CIS 8080 IS Security & Privacy (3cr)
CIS 8045 Unstructured Data Management (3cr)
CIS 8690 Topics in Information Systems (3cr)
SPRING 2026 - Current (10 cr)
TECH 60300 Graduate Seminar - Planning (1cr)
STAT 52000 Time Series & Applications (3cr)
CS 59300 Computer Vision (3cr)
ECE 59500 Selected Topics in ECE (3cr)
FALL 2026 - Core / Methods (10 cr)
MET 52700 Technology: Global Perspective (3cr)
STAT 50100 Experimental Statistics I (3cr)
TECH 60100 Research Seminar in Technology (1cr)
TECH 64600 Analysis of Research in Industry (3cr)
SPRING 2027 - Advanced Methods (9 cr)
TECH 67600 Analysis of Research Methods (3cr)
CS 57800 Statistical Machine Learning (3cr)
CS 52000 Computational Optimization (3cr)
SUMMER 2027 - Final Prep Load (6 cr)
STAT 51400 Design of Experiments (3cr)
CS 58000 Algorithm Design & Analysis (3cr)
Reading-list drafting and committee/POS audit
FALL 2027 - Final Coursework + Prelim (6 cr)
STAT 52400 Applied Multivariate Analysis (3cr)
ECE 57000 Artificial Intelligence (3cr)
GRAD 68900 CSE Seminar (0cr)
Written prelim, oral prelim, Form 10
SPRING 2028 - FALL 2029 - Research Completion
Sp'28: proposal writing; retake window only if needed
Su'28-Fa'28: proposal completion and defense
Sp'29-Su'29: data collection and analysis
Fa'29: dissertation writing, final defense, ETD
Credit summary: 21 transfer + 41 Purdue coursework + 41 dissertation/research credits = 103 credits listed | Target graduation: Fall 2029

## Slide 6
RESEARCH PHASES, CONTROLS, AND IDP ALIGNMENT
PHASE 1: FOUNDATION
Sp'26 - Sp'27
- Literature review and research problem framing.
- Advisor meetings; first publication idea.
- Build technical base in ML, CV, statistics, optimization.
PHASE 2: QUALIFICATION
Su'27 - Fa'27
- POS/course audit, committee, reading list, written/oral prelim.
- Synthesis-focused study, not memorization-only review.
- Spring 2028 retake window exists only as contingency.
PHASE 3: PROPOSAL
Sp'28 - Fa'28
- Proposal writing, methodology, data protocol, committee feedback.
- IRB or data permissions if required by final design.
- Proposal defense in Fall 2028.
PHASE 4: COMPLETION
Sp'29 - Fa'29
- Data collection and analysis in Spring-Summer 2029.
- Dissertation writing and revisions through Fall 2029.
- Final defense, ETD submission, graduation clearance.
Controls added in Version 4
- Prelim is expanded into a checklist-driven workflow, not a single date.
- Retake contingency is visible but separated from the main success path.
- Research-only semesters are explicit: Sp'29, Su'29, and Fa'29.
- Final defense remains the terminal milestone with ETD/graduation clearance.