## updated
My Graduate Program Timeline - Srishti S Agrawal
Start Date: August 2025
End Date: Spring/ Summer 2028 (Ideal Timeline)
Courses and Research Credits | Status | Year 1 (2025 - 2026) |  |  | Year 2 (2026 - 2027) |  |  | Year 3 (2027 - 2028) |  |  | Year 4
|  | Fall '25 | Spring '26 | Summer '26 | Fall '26 | Spring '27 | Summer '27 | Fall '28 | Spring '28 | Summer '28 | Fall '29
EDPS 533 - Intro to Educational Research 1 | Completed | 3 cr.
EDPS 531 - Intro To Measurement & Instrument Design | Completed | 3 cr.
TECH 676 - Analysis of Research Methods | Completed | 3 cr.
ANTH 605 - Seminar in Ethnographic Methods | Completed | 3 cr.
TECH 603 - Graduate Seminar (Planning) | In Progress |  | 1 cr.
EDCI 615 - Qual Research Methods in Education | In Progress |  | 3 cr.
COM 597 - AI, Communication and Society | In Progress |  | 3 cr.
ANTH 641 - Discovery Design Applied Methods | In Progress |  | 3 cr.
POL 52801 - Org. Gov. of Tech and AI | In Progress |  | 3 cr.
EDCI 616 - Qualitative Data Collection | Planned |  |  |  | 3 cr.
Research Credits | Planned |  |  |  | 6 cr. | 9 cr. |  | 9 cr. | 9 cr.
Dependencies
Plan of Study | In Progress |  | File by end of April 2026
Finalize Committee for Prelims | In Progress |  | Finalize by end of April
Send Domains and Interest Areas for Prelims | Planned |  |  |  | Send by start of Sem.
Complete the Qualitaive Research Certification | Planned |  |  |  | Complete by end of Sem.
Complete Course Requirement | Planned |  |  |  | Complete by end of Sem.
Finalize Committee for Defense | Planned |  |  |  |  | By end of Jan
Milestones
Internship | Planned |  | Interviewing | If possible |  | Apply, Interview | Planned Milestone
Prelims and Contigency Plan for Prelims | Planned |  |  |  | By end of Sem (Nov), ideally | By mid sem (Contigency)
Dissertation Proposal | Planned |  |  |  |  | work, advisor meets | work, advisor meets | By end Sem
Dissertation Data Collection and Analysis (if any) | Planned
Dissertation Writing | Planned
Defense | Planned | [7 empty] | Ideally defend | Or Defend early summer | Or Defend early summer
Job Search (Industry - Preference 1) | Planned | [6 empty] | Apply, Interview | Apply, Interview | Apply, Interview | Apply, Interview
Job Search (Academia - Preference 2) | Alternative Plan |  |  |  | Passive Search, Prepare | Search role, Apply, Prepare | Search role, Apply, Prepare | Search role, Apply, Prepare | Search role, Apply, Prepare
Graduation | Planned | [8 empty] | Ideally graduate | Graduate

## old
My Graduate Program Timeline - Srishti S Agrawal
Start Date: August 2025
End Date: Spring/ Summer 2028 (Ideal Timeline)
Course / Activity / Milestone | Status | Year 1 (2025 - 2026) |  |  | Year 2 (2026 - 2027) |  |  | Year 3 (2027 - 2028)
|  | Fall '25 | Spring '26 | Summer '26 | Fall '26 | Spring '27 | Summer '27 | Fall '28 | Spring '28 | Summer '28
EDPS 533 - Intro to Educational Research 1 | Completed | 3 cr.
EDPS 531 - Intro To Measurement & Instrument Design | Completed | 3 cr.
TECH 676 - Analysis of Research Methods | Completed | 3 cr.
ANTH 605 - Seminar in Ethnographic Methods | Completed | 3 cr.
TECH 603 - Graduate Seminar (Planning) | In Progress |  | 1 cr.
EDCI 615 - Qual Research Methods in Education | In Progress |  | 3 cr.
COM 597 - AI, Communication and Society | In Progress |  | 3 cr.
ANTH 641 - Discovery Design Applied Methods | In Progress |  | 3 cr.
POL 52801 - Org. Gov. of Tech and AI | In Progress |  | 3 cr.
DIS 2026 - First-author paper HAII #1 (submitted, in review) | Milestone (In Review) |  | In Review
DIS 2026 - First-author paper HAII #2 (submitted, in review) | Milestone (In Review) |  | In Review
DRS 2026 - First publication as a PhD Student (second author) | Milestone (Completed) |  | Paper Accepted
Research Paper on HAII #3 (CHI 2027 or Similar) | In Progress, Planned |  | Study Design, Lit Review, Analysis | Analysis, Writing | Submission | Paper in Review
CHI 2027 - RA Research Project Paper HCI | Milestone (Planned) | IRB, Study Design | Recruitment, Interview | Interview, Analysis, Writing | Analysis, Writing, Submission | Paper in Review
Portfolio (Final version) | Milestone (Planned)
EDCI 616 - Qualitative Data Collection | Planned |  |  |  | 3 cr.
MET 527 - Tech from a Global Perspective | Planned |  |  |  | 3 cr.
Complete the Qualitaive Research Certification | Milestone (Planned)
Complete Course Requirement | Milestone (Planned)
Research Credits (at least 30 credits) - Focus on RA/TA work, Research projects, Papers, Dissertation, etc. | Planned
Internship | Milestone (Planned) |  | Applying, Interviewing | If possible |  | Apply, Interview | Planned Milestone
Prelims | Milestone (Planned) |  |  |  | Planning, Working | Defend early semester (February)
Dissertation Proposal | Milestone (Planned)
Dissertation Data Collection and Analysis (if any) | Planned
Dissertation Writing | Planned
Defense | Milestone (Planned) | [7 empty] | Ideally defend | Or Defend early summer
Job Search (Industry - Preference 1) | Milestone (Planned) | [6 empty] | Apply, Interview | Apply, Interview | Apply, Interview
Job Search (Academia - Preference 2) | Alternative Plan |  |  |  | Passive Search, Prepare | Search role, Apply, Prepare | Search role, Apply, Prepare | Search role, Apply, Prepare | Search role, Apply, Prepare
Graduation | Milestone (Planned) | [8 empty] | Graduation (Planned)
REFLECTION:
For this assignment, I used Google Sheets to create my graduate program timeline. Google Sheets meets the core requirements for this task: it supports a multi-year timeline spanning 2025–2028, allows cloud-based collaboration and sharing via a link, is more accessible to my advisor and mentors (compared to other tools where they may have to make an account for viewing or writing comments) and can be exported as a PDF for submission.
Task dependencies are visually represented through color-coded sequential cells that show the progression of activities within each milestone (for example, IRB → Recruitment → Analysis → Writing → Submission; that may happen in both parallel and sequential manner), making the ordering and relationships between tasks legible at a glance.
One key insight I gained from mapping this timeline is how sequentially dependent the PhD journey is; early years are necessarily front-loaded with coursework and requirements, and meaningful research momentum can only build once those clear. What surprised me is how quickly the internship window and job search follow, leaving little buffer between deep dissertation work and professional transition. While the timeline reflects an ideal three-year trajectory, it is designed with flexibility for a four-year path depending on how milestones like paper acceptances and prelims unfold.